## Slide 1: Strategic Initiative Portfolio Tracker
August 18, 2025
Master Tracking and Reporting Tool for SGMC's Strategic Projects

## Slide 2: Executive Overview
Total initiatives in progress: 22 active projects across departments. Status breakdown: 68% on-track, 18% delayed, 14% at risk of missing targets. Key highlights since last review: Completion of phase 1 in Telehealth Expansion ahead of schedule.1 Behavioral Health Program timeline adjusted due to resource constraints. New vendor contracts secured, reducing supply chain risks.
Overview

## Slide 3: Portfolio Overview Chart
Chart: 
| Patient Care | Technology Innovation | Operational Efficiency | Workforce Development | Community Outreach | Other
Channel mix | 30 | 25 | 15 | 12 | 8
Distribution of Initiatives by Strategic Category
Patient Care and Technology Innovation together account for 65% of current initiatives, emphasizing priority areas for growth and impact.
Portfolio

## Slide 4: Initiative Status
Status Tracking
Key strategic initiatives currently underway include Telehealth Expansion, Behavioral Health Program, and Patient Portal Upgrade, each led by senior executives responsible for delivery.
Status categories include On Track, At Risk, and Delayed. Percentage completion ranges from 30% to 65%, reflecting varied stages of project maturity.
Target completion dates span from late 2025 to early 2026, providing a timeline framework for monitoring and adjusting project plans.
Initiative Overview
Current Status & Progress
Target Completion Dates

## Slide 5: Initiative Status
Status Update
Metric | Value | Description
Avg. match-to-contact time (hours) | 48 | Average time taken to connect after a match.
Patient enrollment rate (%) | 75% | Percentage of patients successfully enrolled.
Patient retention rate (%) | 85% | Percentage of patients retained after joining.
Avg. time from match to enrollment | 3 months | Average duration from match to full enrollment.

## Slide 6: Gantt Chart for Project Timelines
Timeline Overview of Active Strategic Initiatives
Analysis and Recommendations
Telehealth Expansion is progressing steadily with key milestones scheduled through Q4 2025. Behavioral Health Program shows delays in initial phases, requiring timeline adjustments. Resource overlap between initiatives in Q3 2024 suggests need for prioritization and additional staffing. Regular updates to the Gantt chart are essential for proactive risk management and timeline adherence.
Chart: 
| Telehealth Expansion | Behavioral Health Program | Chronic Care Management | Patient Safety Improvement | Health IT Upgrades
Month 1 | 1 | 0 | 0 | 0 | 0
Month 2 | 1 | 0 | 0 | 0 | 0
Month 3 | 1 | 0 | 0 | 1 | 0
Month 4 | 1 | 0 | 1 | 1 | 0
Month 5 | 1 | 0 | 1 | 1 | 0
Month 6 | 1 | 1 | 1 | 1 | 0
Month 7 | 1 | 1 | 1 | 1 | 1
Month 8 | 1 | 1 | 1 | 1 | 1
Month 9 | 0 | 1 | 1 | 1 | 1
Month 10 | 0 | 1 | 1 | 1 | 1
Month 11 | 0 | 1 | 1 | 1 | 1
Month 12 | 0 | 1 | 0 | 1 | 1
Project Tracking

## Slide 7: Budget Tracking
Telehealth Expansion: Budget $3.5M, Actual Spend $2.8M, 80% utilized, on track financially. Behavioral Health Program: Budget $4.2M, Actual Spend $4.8M, 114% utilized, currently over budget due to increased vendor costs. Infrastructure Upgrade: Budget $2.0M, Actual Spend $1.6M, 80% utilized, spending aligns with project timeline. Patient Portal Enhancement: Budget $1.5M, Actual Spend $1.4M, 93% utilized, controlled budget with efficient resource use. Community Outreach Initiative: Budget $900K, Actual Spend $850K, 94% utilized, slightly under budget, good cost management.
Budget

## Slide 8: High-Priority Initiative Deep Dive: Telehealth Expansion
Initiative Deep Dive
Key Milestones Achieved
Completed platform upgrade by Q1 2024, launched pilot program in two regions, secured vendor contracts for new telehealth tools, and trained 50+ clinicians on platform usage.
Current Risks
Potential delays in software integration, clinician adoption rates lower than expected, and regulatory compliance updates pending review.
Dependencies
Dependent on IT infrastructure upgrades, vendor delivery timelines, and ongoing staff training programs to maintain momentum and ensure quality service.
Next Steps
Finalize full rollout plan by Q3 2024, monitor user feedback closely, enhance cybersecurity measures, and prepare detailed progress report for next quarterly review.

## Slide 9: High-Priority Initiative Deep Dive: Behavioral Health Program
Initiative Deep Dive
Key Milestones
Major milestones include completing clinical protocol design by March 2024, launching pilot sites by June 2024, and full program rollout planned for December 2024.
Risks & Challenges
Primary risks involve staffing shortages in behavioral health specialists and delays in EHR integration; mitigation includes hiring initiatives and phased software deployment.
Dependencies
Critical dependencies include coordination with IT for EHR customization, collaboration with clinical teams for training, and vendor support for telehealth platform enhancements.
Performance Metrics
Success will be measured by patient engagement rates, reduction in appointment wait times, and improved clinical outcome scores tracked quarterly.

## Slide 10: Risks & Mitigation Strategies
Risk Management
Limited availability of qualified staff can delay project milestones and reduce productivity, especially in specialized healthcare roles critical for initiatives.
Delays from external vendors can impact supply chains, software delivery, or service implementation, causing timeline slippage and budget overruns.
Complex integration of new healthcare IT systems with legacy platforms can cause downtime or data inconsistencies, risking project success.
Staffing Shortages
Vendor Delays
Tech Integration Issues
Float pool expansion plan Cross-training programs Temporary staffing contracts Regular workforce capacity assessments
Secondary vendor contracts Vendor performance monitoring dashboard Escalation protocols Regular vendor status reviews
Comprehensive IT testing schedule Dedicated integration team Risk assessment and contingency plans Regular stakeholder communication
01
02
03

## Slide 11: Resource Allocation Overview
Clinical Department Hours
Chart: 
| IT Department | Clinical Department | Operations Department
Hours | 1200 | 980 | 620
IT Department Hours
1200
980
Operations Department Hours
620
Resources
Staff Time Dedicated by Department (Hours, Quarterly)

## Slide 12: Next Steps & Action Items
Approve additional resource allocation for high-priority initiatives facing staffing shortages.
Authorize contingency budget release to address vendor delays and unforeseen expenses.
Review and endorse revised timelines for initiatives currently at risk of delay.
Confirm leadership support for enhanced cross-departmental collaboration on critical dependencies.
Set dates for follow-up reviews to monitor progress on action items and risk mitigation efforts.
Action Plan

## Slide 13: Appendix
PMO Detailed Documentation: Comprehensive reports on project plans, timelines, and status updates available on the SGMC intranet.
Strategic Plan Documents: Reference materials outlining SGMC’s long-term goals, priorities, and performance metrics. -Budget Reports: Quarterly financial summaries detailing budget allocation, actual spend, and variance analyses. -Risk Management Logs: Up-to-date records of identified risks, mitigation strategies, and impact assessments. -Resource Allocation Data: Department-wise staffing and resource distribution reports to track capacity and utilization.
Appendix