## Slide 1: Strategic Initiative Portfolio Tracker
Quarterly Leadership Review – April 26, 2024

## Slide 2: Overview
Total initiatives in progress: 25 active projects across multiple departments. 70% of initiatives are on track, 15% delayed, and 15% currently at risk.
Key highlights include successful launch of the Telehealth Expansion pilot and progress in Behavioral Health Program despite resource constraints. -Recent delays primarily due to vendor-related issues and staffing shortages in critical areas. -Focused mitigation plans are being implemented to address at-risk projects and improve overall delivery timelines.
Overview
Notes: This tracker provides leadership with a consolidated view of all active and planned initiatives, highlighting which projects are on track, delayed, or at risk. It ensures visibility across departments and allows leaders to align resources with SGMC’s long-term strategy.

## Slide 3: Portfolio Overview
Initiatives by Strategic Category
Key Insights from Portfolio Distribution
Patient Care Innovation accounts for 35% of initiatives, emphasizing SGMC’s focus on improving clinical outcomes and patient experience. Digital Transformation makes up 30%, highlighting investments in technology upgrades and telehealth capabilities. Operational Excellence initiatives represent 20%, aiming to optimize processes and reduce costs. Workforce Development and Community Outreach combined constitute 15%, supporting staff growth and community health engagement.
Chart: 
| Patient Care Innovation | Digital Transformation | Operational Excellence | Workforce Development | Community Outreach | Other
Channel mix | 35 | 30 | 20 | 10 | 5
Overview
Notes: By organizing initiatives by category, we can see where SGMC is investing the most time and resources. This helps identify strategic priorities, balance the portfolio, and ensure that projects support both clinical and financial goals

## Slide 4: Initiative Status
Initiative Status
Owner: CIO. Status: On Track. 65% complete with a target completion date of 11/30/2025.
Owner: CMO. Status: At Risk. 45% complete with a target completion date of 03/31/2026.
Telehealth Expansion
Behavioral Health Program
Owner: CTO. Status: Delayed. 50% complete with a revised target date of 12/15/2025.
Owner: CIO. Status: On Track. 70% complete, aiming to finish by 10/20/2025.
Patient Portal Upgrade
Electronic Medical Records Integration

## Slide 5: Initiative Status Table 2
Initiative Status
Community Health Outreach
Owner: Director of Community Services. Status: On Track. Completion: 70%. Target Date: 09/30/2025.
EHR System Upgrade
Owner: CIO. Status: Delayed due to vendor issues. Completion: 50%. Target Date revised to 12/31/2025.
Patient Experience Enhancement
Owner: Chief Nursing Officer. Status: On Track. Completion: 60%. Target Date: 07/31/2025.
Data Analytics Platform
Owner: Chief Data Officer. Status: At Risk due to resource constraints. Completion: 40%. Target Date: 10/15/2025.
01
03
02
04

## Slide 6: Initiative Status Table
Initiative Status
No. | Project | Owner | Status | % Complete | Target Date
01 | Community Health Outreach | Director of Community Programs | On Track | 70% | 09/30/2025
02 | Electronic Health Records Upgrade | CIO | Delayed | 55% | 12/15/2025
03 | Patient Experience Enhancement | Chief Nursing Officer | At Risk | 40% | 06/30/2026
04 | Sustainability & Waste Reduction | Facilities Manager | On Track | 60% | 08/31/2025
Notes: Each initiative is tracked by owner, completion percentage, and target date, giving a clear picture of accountability and progress. The Gantt chart and status tables make it easy to spot risks early and take corrective action.

## Slide 7: Project Timelines Gantt Chart
Detailed milestone tracking highlights critical path activities to ensure timely project delivery.
Chart: 
| Telehealth Expansion | Behavioral Health Program | Infrastructure Upgrade
Start Month | 1 | 5 | 3
Duration (Months) | 18 | 22 | 20
Timeline
Gantt Chart Showing Timelines and Milestones for Key Initiatives

## Slide 8: Budget Tracking Table
Budget Monitoring
Budget Overview
Total allocated budget for strategic initiatives is $12 million, with 60% already committed across projects.
Actual Spend to Date
Actual expenditures have reached $7.2 million, representing 60% of the total budget, aligning with project progress.
Variance Analysis
Current variance is minimal at 2%, with slight overspend in Behavioral Health and savings in Telehealth Expansion.
Financial Risks
Potential vendor delays and staffing cost increases may impact future spend projections; contingency funds are reserved.
01
03
02
04
Notes: Budget tracking compares planned spending with actual costs, helping finance leaders ensure fiscal responsibility. Resource allocation charts show how staff time is distributed, making it easier to adjust workload and address capacity gaps

## Slide 9: High-Priority Initiative Deep Dive: Telehealth Expansion
Deep Dive
Completed technology platform upgrade by Q1 2024. Launched pilot program with 3 regional clinics in Q2 2024. Expanded patient access to telehealth services by 40% as of Q3 2024.
Potential technology integration issues with legacy systems. Risk of patient engagement decline if user experience is not optimized. Regulatory changes may impact telehealth reimbursement policies.
Reliance on IT department for seamless platform integration. Coordination with clinical teams for training and workflow adaptation. Vendor support for software maintenance and updates.
Key Milestones
Risks
Dependencies

## Slide 10: High-Priority Initiative Deep Dive: Behavioral Health Program
Completed initial patient needs assessment and community outreach. Secured funding approval and initiated vendor contracts. Launch of pilot program scheduled for Q3 2024 with full rollout targeted by Q1 2026.
Staffing shortages in behavioral health specialists pose a challenge. Potential vendor delays in software delivery could impact timelines. Regulatory changes may require adjustments in program scope.
Dependent on IT infrastructure upgrades for telehealth integration. Coordination required with regulatory bodies for compliance approvals. Collaboration with community health partners essential for outreach success.
Key Milestones
Risks
Dependencies
Deep Dive

## Slide 11: High-Priority Initiative Deep Dive: Third Initiative
Deep Dive
Completed initial stakeholder alignment, finalized vendor contracts by Q2 2024, and launched phase 1 pilot in select departments with successful feedback.
Potential regulatory delays due to new compliance requirements; risk of resource constraints from overlapping projects; mitigation plans include early engagement with compliance team and resource reallocation.
Dependent on IT infrastructure upgrades scheduled for Q3 2024, vendor deliverables for software integration, and cross-department cooperation for data sharing and training.
Key Milestones
Risks
Dependencies

## Slide 12: Risks & Mitigation Strategies
Staffing shortages impacting project timelines – mitigation through expansion of the float pool and cross-training staff.
Vendor delays causing potential bottlenecks – mitigation by establishing secondary vendor contracts and regular performance reviews.
Budget overruns due to unforeseen expenses – mitigation via stringent budget monitoring and contingency funds allocation.
Technology integration challenges – mitigation by phased rollouts and dedicated IT support teams. Regulatory changes affecting project scope – mitigation through ongoing compliance monitoring and adaptive project planning.
Risks
Notes: Risk logs highlight common challenges such as staffing shortages and vendor delays, along with mitigation plans. Next steps outline leadership decisions needed to keep initiatives moving forward, ensuring accountability and timely execution.

## Slide 13: Resource Allocation Overview
Staff Time Dedicated by Department
Resource Distribution Analysis
Nursing dedicates the highest staff time, reflecting frontline project needs and patient care integration. IT department follows closely, supporting technical infrastructure and telehealth initiatives. Operations and Finance contribute significantly to project management and budget oversight. Smaller allocations from HR and Marketing support staffing and communication efforts respectively.
Chart: 
| Nursing | IT | Operations | Finance | HR | Marketing
Staff Hours | 320 | 290 | 180 | 150 | 90 | 70
Resources

## Slide 14: Next Steps & Action Items
Approve additional resource allocation for high-risk initiatives to address staffing shortages.
Confirm timeline adjustments for delayed projects to align with updated risk assessments.
Authorize budget reallocations based on the latest spend vs. forecast analysis. Endorse the proposed mitigation strategies for vendor and supply chain delays. Schedule the next quarterly review meeting and define key performance indicators for progress tracking.
Action

## Slide 15: Appendix
SGMC PMO Dashboard: Comprehensive tracking of all active and planned initiatives with real-time updates.
Strategic Plan Document 2024–2028: Provides organizational goals and alignment criteria for initiatives.
Quarterly Budget Reports: Detailed financial data comparing budgeted versus actual spend per initiative.
Risk Management Logs: Updated risk registers with mitigation actions and impact assessments. Resource Allocation Records: Documentation of staff assignments, time tracking, and departmental resource distribution.1